## Slide 1: Story-Based Burn Down
Case Study and Discussion

## Slide 2: Scrum Team Pains
Scrum team (at least our team) pains:
Obsesses over sprint planning, especially the task estimates
  Long, boring meetings
  Big estimation gap between different individuals
Hard to measure true feature completion using burn down chart
  # of hours spent cannot represent # of feature completed
  Team still concerned about the commitment even if the burn down looks good
Hard to measure the true velocity
  If we measure velocity by actual hours the team spent, possibly the velocity will be pretty high even if nothing is done
  Hours look more like “capacity” rather than velocity

## Slide 3: Situation in our Sprint # 1
We spent 6 hours in our 2-week sprint’s planning meeting
The burn down chart looked good but the feature completion was bad
We used actual hours to measure velocity, but by the end of sprint # 1 we were not confident to use that velocity to make the commitment for the next sprint
Iteration Burn Down Chart
297
279.5
249.5
196.5
180 180
125.5
105 105
81.5
67.2
300
270
240
210
180
150
120
90
60
30
0
Monday Tuesday WednesdayThursday Friday Saturday Sunday Monday Tuesday WednesdayThursday Friday
Week 1 Week 2
Date
Hours
Features Delivered
10 10 10 10 10
9 9 9
8 8
7 7
11
10
9
8
7
6
5
4
3
2
1
0
Monday Tuesday WednesdayThursday Friday Saturday Sunday Monday Tuesday Wednesday Thursday Friday
Week1 Week 2
Date
Hours

## Slide 4: Key Problems we want to resolve
Seems all the problems are related to “hours”:
Hard to use hours to size the stories/tasks
Hard to associate the time-based burn down with the feature completion
– Using actual hours to measure true velocity is not the best solution – how many hours the team can burn has no direct relationship between the commitment which is the final delivery

## Slide 5: Our solution for resolving the issues
Story Points is a better choice for the estimates
  Published research shows that humans are terrible at estimating anything in hours ¹
  The tasks which one team/individual can finish in 10 hours may cost 100 hours for another team/individual
  Story Points is the absolute value for the size of the Product Backlog Items (PBIs)
Task-based burn down could represent true completion
  No direct relationship between time spent and feature completion
  Task-based burn down should be more meaningful
  Key dependency is a clear “definition of done” for the tasks
Use story points to measure the velocity
  Velocity is how many story points a team can deliver in one sprint, not how many hours a team can burn
  We can use “Story Points finished/sprint” as the formula when calculating the velocity
[1] - See the references

## Slide 6: Improvement Plan for Sprint # 2
Action | Description
1. Improve the Task Break Down | 1) Decompose the final deliverables into small pieces, create one task for each small piece
 | 1) Define "done" for each task - ensure the completion of each task means the delivery of one potential shippable product
1. Use Story Points for estimation | 1) Select one “ template story” as the standard criteria
 | 1) Get the story points for each task based on the comparison with the template story, but still estimate how many ideal hours we need to finish that task
1. Use the Task-based Burn Down for tracking | 1) Start to use Task-based Burn Down (still use Time-based burn down at the same time)
 | 1) Record the actual hours we spent to finish the tasks
1. Measure velocity using story points finished/sprint | 1) After we get stable team velocity, then stop doing estimates using hours, stop using actual hours to measure velocity

## Slide 7: Our practice in Sprint # 2
Spent 4 hours for the sprint planning
Improved task break down and definition of “done”
Created template story and estimated all the tasks using Story Points
Established task-based burn down chart
task-based burn down chart
28
30
40 40
41
33
30
27
24
26
29
22
15
11
3
50
45
40
35
30
25
20
15
10
5
0
Week1
Week2
Hours
time-based burn down chart
184 183
163 165.5
144.5
123.5
114
101
83.2
63.7 60.9
200
180
160
140
120
100
80
60
40
20
0
27.4 20.7 19.7
4.5
MondayTuesdaWyednesdTahyursdayFridayMondayTuesdaWyednesdTahyursdayFridayMondayTuesdaWyednesdTahyursdayFriday
Week1 Week2
Hours

## Slide 8: Benefit of using new approach
 In general, the task-based burn down matches the feature completion
– Which means the chart can represent the real velocity
task-based burn down chart
28
30
40 40
41
33
30
27
24
26
29
22
15
11
3
50
45
40
35
30
25
20
15
10
5
0
Week1
Week2
Hours
spring # 2 feature completion
11
10
8 8
7
6 6
5
4
2 2
1
12 12 12
11
10
9
8
7
6
5
4
3
2
1
0
0
MondayTuesdaWyednesdTahyursdayFridayMondayTuesdaWyednesdTahyursdayFridayMondayTuesdaWyednesdaTyhursdayFriday
Week 1 Week 2
Remaining Features

## Slide 9: New challenges

Task-based burn down is still not good enough to represent feature completion
Tasks are too detailed - the # of tasks kept increasing, it’s hard (and not necessary) to identify all the related tasks to complete one story in sprint planning meeting
Too many dependencies between different tasks and also we had lots of generic tasks like document writing/regression testing
task-based Iteration Progress
29
35
45
50
52
53
55
59 60
65
70
66
67
70
71
1
20
25
32
36
39
41
44
52
59
68
0
10 10 11
5 5
20
30
40
50
60
80
70
Monday
Tuesday
Wednesday
Thursday
Friday
Monday
Tuesday
Wednesday
Thursday
Friday
Monday
Tuesday
Wednesday
Thursday
Friday
Week 1
Week 2
Hours
task-based burn down chart
28
30
40 40 41
33
30
27
24
26
29
22
15
11
3
50
45
40
35
30
25
20
15
10
5
0
Week1
Week2
Hours

## Slide 10: Our solution for the new challenges
Use story-based burn down instead of task-based burn down
  Tasks are so detailed that sometimes we can not say they are potential shippable deliverables
  But obviously one story is a potential shippable deliverable
  Story-based burn down and task-based burn down are essentially the same

## Slide 11: Next step
Action | Description
Continue to improve the Task Break Down | 1. Scale down the size of each story, use “stories” to represent small features, e.g., small enough for one developer to finish in 2-3 days
 | 1. Need a clear definition of done for each story – usually use passing FT/ UAT without Major and above defects as the exit criteria
Estimate the size of each story | Use story points to estimate the size of each story, but DON’T do estimate for all the tasks
Use the story-based Burn Down for tracking | 1. Still use 2 burn down charts at the same time: story-based burn down and effort-based burn down.
 | Only deduct the estimated story points when the corresponding stories are Completely Finished – meet the definition of done
 | 1. Record the actual hours only for reference, and calculate how many stories (or story points) team can finish in one sprint as the true velocity

## Slide 12: One sample sprint - sprint backlog (mock up)
Story | Est. Points | Task | Task Act Hours | Story Act Hours | Done
Story # 1 | 8 | Requirement review + Test Case Development | 1 | 11 | √
 |  | Front-end code + Selenium Test | 3 |  | 
 |  | UT + Back-end code | 4 |  | 
 |  | Integration + Integration Test | 3 |  | 
Story # 2 | 5 | Requirement review + Test Case Development | 1 | 8 | √
 |  | Front-end code + Selenium Test | 3 |  | 
 |  | UT + Back-end code | 1 |  | 
 |  | Integration + Integration Test | 3 |  | 
Story # 3 | 13 | Requirement review + Test Case Development | 2 | 18 | √
 |  | Front-end code + Selenium Test | 0 |  | 
 |  | UT + Back-end code | 8 |  | 
 |  | Integration + Integration Test | 8 |  | 
 |  | …… |  |  | 
Story # 15 | 5 | Requirement review + Test Case Development | 1 | 7 | √
 |  | Front-end code + Selenium Test | 2 |  | 
 |  | UT + Back-end code | 2 |  | 
 |  | Integration + Integration Test | 2 |  | 
400
120
Total:

## Slide 13: One possible sample sprint - Metrics
Date |  | Total Stories | Rem. Est. Stories Points |  | Burned Points | Rem. Points | Actual Hours Act Hr/D |  | Points/D
Week 1 | Monday | 15 | 15 | 105 | 0 | 105 | 8 | 2.00 | 0.00
 | Tuesday | 15 | 15 | 105 | 0 | 105 | 20.8 | 2.60 | 0.00
 | Wednesday | 15 | 14 | 110 | 13 | 97 | 34 | 2.83 | 4.33
 | Thursday | 15 | 12 | 110 | 31 | 79 | 48 | 3.00 | 7.75
 | Friday | 15 | 11 | 113 | 36 | 77 | 61.6 | 3.08 | 7.20
Week 2 | Monday | 15 | 8 | 115 | 46 | 69 | 82 | 3.42 | 7.67
 | Tuesday | 15 | 6 | 118 | 57 | 61 | 101.6 | 3.63 | 8.14
 | Wednesday | 15 | 4 | 115 | 64 | 51 | 118.4 | 3.70 | 8.00
 | Thursday | 15 | 2 | 120 | 85 | 35 | 136.8 | 3.80 | 9.44
 | Friday | 15 | 0 | 120 | 120 | 0 | 152.4 | 3.81 | 12.00

## Slide 14
Story Burn Down Chart
15 15
14
12
11
8
6
4
2
0
16
14
12
10
8
6
4
2
0
Monday
Friday
Tuesday Wednesday Thursday
Week 1
Tuesday Wednesday Thursday
Week 2
Friday Monday
Date
Stories
Remaining Stories

## Slide 15: Story Point Burn Down Chart
105 105
97
79
77
69
61
51
35
0
110
99
88
77
66
55
44
33
22
11
0
Monday
Tuesday
Tuesday
Friday
Wednesday Thursday
Week 1
Wednesday Thursday
Week 2
Friday Monday
Date
Story Points
Remaining Story Points

## Slide 16: Sprint Progress Chart
105 105
110 110
113
115
118
115
0
0
13
31
36
46
57
64
85
120 120
160
144
128
112
96
80
64
48
32
16
0
Monday
Friday
Tuesday Wednesday Thursday
Week 1
Tuesday Wednesday Thursday
Week 2
Friday Monday
Date
Story Points
Est. Story Points
Burned Story Points

## Slide 17: Time Based Progress vs. Story Point Based Progress
0
0
13
31
36
46
57
64
85
120
8
20.8
34
48
61.6
82
101.6
118.4
136.8
152.4
160
144
128
112
96
80
64
48
32
16
0
Monday Tuesday Wednesday Thursday
Friday
Monday Tuesday
Wednesday Thursday
Friday
Week 1
Week 2
Date
Hours
Effort Based Burn Down
Story Point Based Burn Down

## Slide 18: sample sprint - Charts
Story Burn Down Chart
15 15
14
12
11
8
6
4
2
0
16
14
12
10
8
6
4
2
0
Monday Tuesday Wednesday Thursday Friday Monday Tuesday Wednesday Thursday Friday
Week 1
Week 2
Date
Stories
Remaining Stories
Story Point Burn Down Chart
105 105
97
79
77
69
61
51
35
110
99
88
77
66
55
44
33
22
11
0
0
Monday Tuesday Wednesday Thursday Friday Monday Tuesday Wednesday Thursday Friday
Week 1
Week 2
Date
Story Points
Remaining Story Points
Sprint Porgress Chart
105 105
110 110
113
115
118
115
0 0
13
31
36
46
57
64
85
120 120
160
144
128
112
96
80
64
48
32
16
0
Monday Tuesday Wednesday Thursday Friday Monday Tuesday Wednesday Thursday Friday
Date
Story Points
Week 1
Est. Story Points
Week 2
Burned Story Points
Time Based Progress vs. Story Point Based Progress
0
0
13
31
36
46
57
64
85
120
8
20.8
34
48
61.6
82
101.6
118.4
136.8
152.4
160
144
128
112
96
80
64
48
32
16
0
Monday Tuesday Wednesday Thursday Friday
Monday
Tuesday Wednesday Thursday
Friday
Week 1 Week 2
Date
Hours
Effort Based Burn Down Story Point Based Burn Down